## Summary_Ack
| Location / URL Details | Sheefa | Sathish
Framework KT | Done | I Acknowledge
Application : Ebundle, ICDD, EBBS, ICM | Done | I Acknowledge(ICM,ICDD)
Application : RTOB | Done | I Acknowledge
Application : COS, SAO | System not yet available | system unavialable
ICDD Suite : Sharepath Location | Stash Path is shared with team | I Acknowledge | I Acknowledge
RTOB Suite : Sharepath Location | Stash Path is shared with team | I Acknowledge | I Acknowledge
Recording Videos | \\inhadfil101\wkgrps7\ICDD UAT project team\SCB_Automation | I Acknowledge | I Acknowledge
Confluence Page details | Shared with Team already | I Acknowledge | I Acknowledge
Service Request for softwares | Shared with Team already | I Acknowledge | I Acknowledge
SCB Contact List of Peoples with Mail id and Phone | Shared to Sheefa | I Acknowledge | I Acknowledge
All Interim Traceability work items created | \\inhadfil101\wkgrps7\ICDD UAT project team\Karthik VV\Traceability | I Acknowledge | I Acknowledge
Stash ( Test Cases to be downloaded from Stash ) | Stash link will be available in JIRA | I Acknowledge | I Acknowledge
Git - | Shared with Team already | I Acknowledge | I Acknowledge
Jira details ( Access, Test Location , documents, Defects ) | Done | I Acknowledge | I Acknowledge
Defect ( defect numbers identified through automation ) | Will be difficult to track since RTOB Project was closed
Method Lists | Shared with Sheefa | I Acknowledge
All Item mentioned in the KT_PLAN sheet | Done | I Acknowledge
Backlog - Excel sheets ( ICDD, RTOB, RTOB - HK, RTOB - India ) | Anshu has the tracker
Clarification Tracker | \\inhadfil101\wkgrps7\ICDD UAT project team\Karthik VV\Clarification | I Acknowledge | I Acknowledge
Important Mails to be shared to Sathish | Shared already | I Acknowledge | I Acknowledge
Dump of Karthik & Swati's Folder | Dumb available in common share path | I Acknowledge | I Acknowledge

## KT_PLAN
Date | Subject - Desc | Items to be Explained | Hours Planned | Actual Hours
2018-10-24 | KT on Cucumber and Genie Framework |  | 1 | 1.5
1. Basic brushup on Cucumber
2. Architecture of genie framework
3. Genie Test - Runner Class
4. How to pass data from excel using fillo
5. What is cucumber options and how to use tags
6. How to set path for glue and usage of other available cucumber options
7. Reporting used in Genie framework
8. Detailed Navigation and structure of framework
2018-10-25 | Genie Framework Discussion(Addressing Framework related queries) |  | 1 | 1
1. How to set property file path and where to update URL and user credentials for login
2. Log4j Implementation
3. Detailed explanation on How to use framework, Where to create objects, Implementation of gherkin steps, common method utils.
4. Addressing queries on Sheefa's doubts
2018-10-26 | KT On ICM Application |  | 1 | 1
1. How to do profile enquiry of a ICM Customer
2. Basic customer details, products, Risk codes
3. What is Prohibition when it will be created.
4. Different levels of risk rating for a customer
5. How to modify a customer profile and approve it using checker
2018-10-29 | KT On ICDD Application |  | 1 | 1
1. How to search customer records and alerts
2. Manual Trigger Review
3. Periodic Trigger Review
4. Next step and mandatory e-checks
2018-10-30 | KT On ICDD Application |  | 1 | 1
5. TRR Workflow for D (CDD Assigner, SAT Checker, Business Head, Consolidator)
6. Create Review Checklist e-form Creation and Completion of workflow
7. How to clone a form
2018-10-31 | KT On ICDD Application |  | 1 | 1
8. SOW e-form Creation and Completion of workflow
9. PEP e-form Creation and Completion of workflow
10. Tax e-form Creation and Completion of workflow
11. Adverse Media e-form Creation and Completion of workflow
12. Client Contact e-form Creation and Completion of workflow
13. Data Sync script
2018-11-01 | KT On ICDD Application |  | 1 | 1
14. TRR Workflow for A & B rating (STP process)
15. What is prohibition and reasons for it (SOW, PEP, Adverse, Sanctioned Country)
2018-11-02 | KT On ICDD Application |  | 1 | 1
16. How to assign the alert to a specific User
17. ICDD Navigations and UI accessiblity
18. TRR. Workflow (C & D)
2018-11-05 | KT on Onboarding application (RTOB) |  | 1 | 2
1. How to onboard a customer
2. Explain different workbaskets, functionality
3. CDD Risk Rating and Fullfilment
4. Different products (CASA, CC, PL)
2018-11-07 | KT on Onboarding application (COS) |  | 1 | 1.5
1. Explain CC product and workflow
2018-11-08 | KT on how to raise IT Service Request in SCB and other IT related process |  | 0.5 | 0.5
1. How to raise software request ticket
2. How to enhance system performance (Msconfig, Temp)
2018-11-09 | KT on what scripts have been created for IN and HK and how to use it |  | 1 | 0.5
1. How to use common functionality of IN and HK in scripts
2. Understanding the gherkins written for IN and HK
2018-11-20 | KT on Version controlling system (GIT) |  | 0.5 | 0.5
1. How to create repository
2. How to get status, add all files
3. How to commit and push the new code into repository
2018-11-21 | Details of R0 and R1 Testing of HK/INDIA and list of methods/scenarios created as part of the automation |  | 0.5 | 0.25
1. What are the different Rounds of testing in HK/INDIA
2. List of methods created for HK and INDIA
3. List of scenarios created for HK and INDIA

## Reverse_KT
Date | Subject - Desc | Hours Planned | Actual Hours | Comments
2018-11-12 | Reverse_KT on Cucumber and Genie Framework | 1 | 1 | Framework PPT has been shared and Sheefa has prepared understanding document for it.
2018-11-14 | Reverse KT On ICM Application | 1 | 0.5
2018-11-15 | Reverse KT on RTOB Application | 1 | 1
2018-11-27 | Reverse KT On ICDD Application | 1 | 1.5 | Handson and workflow completion was explain clearly
2018-11-28 | Reverse KT on Usage of methods in HK/INDIA | 1 | 1 | Each method purpose is been noted and documented